## Feuil1
| phase,stage,Time period etc |  | last updated: DATE IN HERE |  | JUNE |  |  | JULY |  |  |  |  | AUGUST
Period | Tasks | Description of Project Steps | Status | Who | June 10-16 | June 17-23 | June 24-30 | July 1-7 | July 8-14 | July 15-21 | July 22-28 | July 29 - Aug 4 | Aug 5-11 | Aug 12-18 | Aug 19-25 | Aug 26-31
Week 1 | Preparation and Configuration
Days 1-2 | WordPress Installation and Hosting | Install WordPress on the selected hosting server |  | Name
Days 3-4 | Choose and Install a Theme | Select and install an appropriate theme for the website |  | Name
Days 5-7 | Install Necessary Plugins | Install the required plugins for the desired functionalities on the site |  | Name
Week 2 | Landing Page and Capture Page Creation
Days 8-10 | Create the Landing Page | Design and develop the landing page to welcome visitors | In progress / | Name
Days 11-14 | Create the Capture Page | Design and develop the page to capture visitors' information | In progress / | Name
Week 3 | Integration and Automation
Days 15-17 | Integrate with Odoo | Connect the website with the Odoo ERP system for integrated management | In progress | Name
Days 18-21 | Choose and Configure an Email Marketing Service | Select and configure an email marketing service (like Mailchimp, Sendinblue) | In progress | Name
Week 4 | Content Creation and SEO
Days 22-24 | Create Blog Content | Write and publish relevant content for the site's blog | In progress | Name
Days 25-28 | SEO Optimization of the Site | Optimize the site for search engines to improve ranking | In progress | Name
Week 5 | Email Campaign Configuration
Days 29-32 | Create Automated Email Sequences | Design and configure email sequences for customer engagement | In progress | Name
Days 33-35 | Configure Automation in Odoo | Set up automated processes in Odoo for email and customer management | In progress | Name
Week 6 | Advertising and Social Media
Days 36-38 | Launch Advertising Campaigns | Create and launch advertising campaigns on chosen platforms | In progress / Name | Name
Days 39-42 | Plan and Post on Social Media | Plan and post content on social media to increase visibility | In progress / Name | Name
Week 7 | Webinars and Consultations
Days 43-45 | Organize Webinars | Plan and organize webinars for clients and prospects | In progress / Name | Name
Days 46-49 | Set Up Online Appointment Booking | Set up an online appointment booking system for consultations | In progress / Name | Name
Week 8 | Follow-Up and Loyalty
Days 50-52 | Implement Loyalty Programs | Create and launch loyalty programs for clients | In progress / Name | Name
Days 53-56 | Client Follow-Up and Satisfaction Surveys | Conduct regular client follow-ups and satisfaction surveys | In progress / Name | name
Days 57-60 | Analysis and Adjustments | Analyze the results of different actions and adjust strategies accordingly | In progress / Name | Name